## Tabelle1
Agile meets Security - Weekly recording of activities(0)
Team name: |  | GitGuardians
Name team member A: |  | Karnavat, Aadit
Name team member B: |  | Farag, Beshoy
Name team member C: |  | Guardiola, Antonio Huesa
Name team member D:
Name team member E:
Link to the backlogs: |  | https://agilesecgitguardians.atlassian.net/jira/core/projects/AG/list?sortBy=labels&direction=ASC
Link to the documentation:
Link to the Gitlab project: |  | https://lv-gitlab.intern.th-ab.de/agilesec2025/team14/gitlab-profile
(0) This document must be updated weekly. The current version must be submitted by the Scrum Master in Moodle on Tuesday evening.
(1) The time expected to be contributed per team member per week is approx. 18 hours.
(2) Enter the duration to the nearest half hour (i.e. half an hour equals 0.5; two hours equals 2.0).
Sprint 1, Week 1 - Wednesday, 23.4.2025 to Tuesday, 29.4.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 | Research how to implement CI/CD on GitLab | As a DevOps engineer, I want to understand GitLab CI/CD best practices, so that I can design an efficient and secure pipeline for our applications. | 1
| 2 | Set up GitLab CI/CD Runner | As a DevOps engineer, I want to configure a GitLab Runner for our projects, so that pipelines can automatically execute build and deploy jobs. | 1.5
| 3 | Install GitLab Runner (target: Ubuntu VM) | As a system administrator, I want to install and register GitLab Runner on our Ubuntu VM, so that jobs can be run in a controlled, self-hosted environment. | 0.5
| 4 | Research appropriate tech stack for CI/CD + security tools | As a solution architect, I want to evaluate and choose the right tools (CI/CD, scanners, container engine), so that our pipeline is compatible, scalable, and secure. | 0.5
| 5 | Virtual Machine configuration | As a system admin, I want to configure a VM with required packages and networking, so that it can host Docker containers and GitLab Runner securely. | 1
| 6 | Install Docker Engine on VM | As a DevOps engineer, I want to install Docker on our VM, so that I can use containers to deploy apps and run security scans in isolated environments. | 0.5
| 7 | . Create Dockerfiles for containerization | As a developer, I want to write Dockerfiles for the Todo App and Juice Shop, so that they can be built and deployed in consistent container environments. | 0.5
| 8 | Search GitLab Server Access / Authentication | As a DevOps engineer, I want to verify and set up access to the GitLab server, so that our runner can securely connect and pull repositories to execute CI/CD jobs. | 1
| 9 |  |  | 0
0
0
|  |  | Sum | 6.5
Sprint 1, Week 2 - Wednesday, 30.4.2025 to Tuesday, 6.5.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%: |  | lack of communication
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 | Research for Acceptance Criteria |  | 1
| 2 | Research for Defination of done |  | 1
| 3 | checking the commands and tools required for the CI/CD pipeline of the todolist app |  | 1.5
| 4 | research on ubuntu VM |  | 1
| 5 | Configure properly the gitlab-runner in the VM |  | 0.5
| 6 | Replace base Images with custom Images for future security tools implementation |  | 1
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
0
0
|  |  | Sum | 6
Sprint 2, Week 1 - Wednesday, 7.5.2025 to Tuesday, 13.5.2025
During this week | 3 | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week | 0 | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 | Backlog refinement |  | 3
| 2 | Acceptance Criteria |  | 1.5
| 3 | DoD |  | 1.5
| 4 | Story: As a Security Champion, I want to fix 3 selected vulnerabilities in the Juice Shop and document the fixes according to secure coding guidelines. |  | 2
| 5 | Story: As a Security Champion, I want to research and test if these vulnerabilities can be automatically detected using SAST tools like Semgrep. |  | 1.5
| 6 | Story: As a Security Champion, I want to contribute to the Secure Coding Checklist so developers can avoid these vulnerabilities in future. |  | 1
| 7 | Story: As a DevOps engineer, I want to learn about the chosen container scannning tool for further implementation in our CI/CD pipelines |  | 0.5
| 8 | Story: As a DevOps engineer, I want to research which container scanner tool fits better our use case |  | 1
| 9 | Story: As a DevOps engineer, I want to implement the container scanning tool to our CI/CD pipelines |  | 1
| 10 | Story: As a DevOps, I want to choose the most appropiate SAST tool based on the projects needs |  | 1.5
| 11 | Story: As a DevOps engineer, I want to learn about the chosen SAST tool for further implementation in our CI/CD pipelines |  | 1
|  |  | Sum | 15.5
Sprint 2, Week 2 - Wednesday, 14.5.2025 to Tuesday, 20.5.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 |  |  | 0
| 2 |  |  | 0
| 3 |  |  | 0
| 4 |  |  | 0
| 5 |  |  | 0
| 6 |  |  | 0
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
0
0
|  |  | Sum | 0
Sprint 3, Week 1 - Wednesday, 21.5.2025 to Tuesday, 27.5.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 |  |  | 0
| 2 |  |  | 0
| 3 |  |  | 0
| 4 |  |  | 0
| 5 |  |  | 0
| 6 |  |  | 0
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
0
0
|  |  | Sum | 0
Sprint 3, Week 2 - Wednesday, 28.5.2025 to Tuesday, 3.6.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 |  |  | 0
| 2 |  |  | 0
| 3 |  |  | 0
| 4 |  |  | 0
| 5 |  |  | 0
| 6 |  |  | 0
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
0
0
|  |  | Sum | 0
Sprint 4, Week 1 - Wednesday, 4.6.2025 to Tuesday, 10.6.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 |  |  | 0
| 2 |  |  | 0
| 3 |  |  | 0
| 4 |  |  | 0
| 5 |  |  | 0
| 6 |  |  | 0
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
0
0
|  |  | Sum | 0
Sprint 4, Week 2 - Wednesday, 11.6.2025 to Tuesday, 17.6.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 |  |  | 0
| 2 |  |  | 0
| 3 |  |  | 0
| 4 |  |  | 0
| 5 |  |  | 0
| 6 |  |  | 0
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
0
0
|  |  | Sum | 0
Sprint 5, Week 1 - Wednesday, 18.6.2025 to Tuesday, 24.6.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 |  |  | 0
| 2 |  |  | 0
| 3 |  |  | 0
| 4 |  |  | 0
| 5 |  |  | 0
| 6 |  |  | 0
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
0
0
|  |  | Sum | 0
Sprint 5, Week 2 - Wednesday, 25.6.2025 to Tuesday, 1.7.2025
During this week |  | team members have contributed 100% of the expected time(1).
During this week |  | team members have contributed >100% of the expected time.
During this week |  | team members have contributed <100% of the expected time. |  | What were the reasons for falling below 100%:
| # | Description of the activity | respective user story- or task-ID | Duration of the activity(2)
| 1 |  |  | 0
| 2 |  |  | 0
| 3 |  |  | 0
| 4 |  |  | 0
| 5 |  |  | 0
| 6 |  |  | 0
| 7 |  |  | 0
| 8 |  |  | 0
| 9 |  |  | 0
0
0
|  |  | Sum | 0